## Introduction
PixShot

Introduction :-
PixShot is an Image Annotation Tool.

Estimated Next Release Version,Date :-
Version 0.9 Alpha, January 1st 2015

Current Version :-
In Development

Developed in :-
C++, Qt Framework

Platforms :-
Windows. Linux

## Features List
Feature List

Task No.	Type	Description	Priority	Status	Release	Estimated Time for Completion	Start Date	End Date	Actual Time taken	Progress (%)	Sub Tasks Status (%)	Pre Work Comments	Post Work Comments

1	Design (Art Work)	a) Creating Logo's / b) Creating Icons / c) Website Logo and icons	High	To be Done		8 Hrs (2 Hrs / Day)

2	Implementation	Code Clean up	High	In Progress		1 Hr (Recurring Task)

3	Release	a) Setup Creation / b) License Documents / c) Build and Deploy scripts / d) MD5 Check sum	High	In Progress		4 Hrs					a) Requires R&D task on NSIS installer / b) R&D task on MD5 check sum

4	Implementation	Options Dialog [preferences]	High	In Progress		~ Hrs	31 Aug 2012					a) Design R&D required

5	Implementation	Context Menu to items	Medium	To be Done		~ Hrs

6	Implementation	Keyboard events	Medium	Done		1 Hr

7	Implementation	Feed Back Module	Low	MOVED – Next Release		~ Hrs					a) Networking R&D

8	Implementation	Tray Menu finalization	High	To be Done		2 Hrs

9	Documentation	Code Documentation	High	To be Done		~ Hrs

10	Unit Testing	Unit Testing entire App	High	In Progress		~ Hrs				NA	NA	Involves finding and reporting Bugs

11	Interface	a) Tool Tips / b) Menu Icons / c) Warnings	High	To be Done		~ Hrs

12	Implementation	TODO tasks	High	To be Done		~ Hrs					NA

13	Implementation	Bug Fixing	High	In Progress		~ Hrs					NA

14	Implementation	Zoom Functionality	Medium	Done		2 Hrs			3 Hrs

15	Interface	UI Beautification	High	To be Done		~ Hrs

16	Interface	Tabbing	High	Done		~ Hrs

17	Interface	Check for Updates	Medium	Done		~ Hrs			6 Hrs

18	Interface	Print Option	Medium	Done					Inclusion of various printer options in Preferences

19	Interface	Undo	High	Done		~ Hrs

## Work
Work

Sno	Type	Details	Start Date	End Date	Status	Priority

1	Defect	More than one star appears adjacent file name after undo's and redo's				Low
2	Enhancement	Arrow head should be filled	16 Nov 2014	16 Nov 2014	Completed				Critical
3	Enhancement	toolFrame in a separate tool window				Medium			High
4	Enhancement	Migrate to GITHUB or GITLAB		31 Mar 2015		Critical			Medium
					Low

Notes :- / This sheet is to plan the tasks and track the ongoing the task/defect/feature / Type : Defect, Enhancement, Feature

## Tracker
Work Tracker

Date	Tasks	Time Spent (Hrs)	Comments	Builds Taken

19 Aug 2012	a) Project Management Documentation initiation - 1.5 Hrs / b) Unit Testing / Code Optimization - 0.25 / c) Bugs [1,2] – 0.5 / d) Documentation – 0.25	2.5	Reported 4 Bugs	4
20 Aug 2012	Created Google Code repository and uploaded the Source files	0.5
31 Aug 2012	Updated this document	0.5
8 Sept 2012	Added Exception handling block in AppManager module	0.25		0
9 Sept 2012	Added icon and the Win resource file	0.25		1
16 Sept 2012	Worked on Task 4 – created preferences interface	2	Created .cpp, .h and .ui files	4
19 Sept 2012	As Above	1.5		2
20 Sept 2012	As Above	0.5	Integrated with AppManager	1
22 Sept 2012	As Above	2		4
29 Sept 2012	As Above	2		3
30 Oct 2012	As Above	1.5		2
6 Oct 2012	As Above	1.5		4
7 Oct 2012	As Above; Registered PixShot.org at BigRock.in @ Rs 2766	1.5	Cleaned up AppManager	1
19 Oct 2012	As Above	1		2
3 Dec 2012	As Above	0.5		1
8 Dec 2012	As Above – functionality of second tab of Preferences dialog	2		0
9 Dec 2012	Worked on Networking and XML reading POC – checking version	2		0
11 Dec 2012	POC on Tabbing	1		1
15 Dec 2012	Tabbing Functionality	1.15		3
6 Jan 2013	Tabbing Functionality	1		3
8 Jan 2013	As Above	1		4
12 Jan 2013	As Above	1
13 Jan 2013	As Above	1.5
14 Jan 2013	Worked on About module	1.25
20 Jan 2013		0.5
21 Jan 2013	Uploaded site	1
22 Jan 2013	Worked on defects	1
24 Jan 2013	Worked on defects, Completed Task 6	1
25 Jan 2013	Worked on Textitem font	1
9 Feb	Worked on New Menu	1
10 Feb 2013	As Above	1
18 Feb 2013	Zoom Functionality	1
19 Feb 2013	As Above	1
23 Feb 2013	Fixing Menu and Preferences	1
24 Feb 2013	As Above	1
25 Feb 2013	As Above	1
16 Mar 2013	Enhanced CropItem	2
17 Mar 2013	As Above	2
19 Mar 2013	Fixed disabling menu's	0.5
11 Apr 2013	Add a simple Print Option	0.75
13 Apr 2013	Worked on Observations (fixes)	1
14 Apr 2013	As Above	1.5
20 Apr 2013	As Above	1.5
21 Apr 2013	As Above	1.5
23 May 2013	As Above	1
25 May 2013	As Above	5
30 June 2013	Undo	2
6 July 2013	Task 20 and save indicator functionality	4
28 July 2013	Fixing preferences options	1
4 August 2013	Completed implementing Drag and Drop	0.5
19 Mar 2014	Minor fixes	0.5
27 Apr 2014	Font Color	1
28 Apr 2014	Font Color	0.5
3 May 2014	Check if pix is saved when closed	0.5		1
17 May 2014	Fixed Update check Network issue	0.5
16 Nov 2014	Worked on Work item 2	0.5	Needs check-in	3

## R&D Tracker
Research & Development Work Track

Date	Tasks	Time Spent (Hrs)

9 Dec 2012	Networking and XML reading	2
11 Dec 2012	POC on tabbing	1
NA	CropItem Graying out	2
28 July 2013	Drag and Drop	1

## Blockers
Blockers

SL No.	Description	In Release	R&D required ?

## Wish List
Wish List

Wish	Target Release	Comments

Check for already open instance when opening	2
Gradients fill (inside items)	2
Text inside items
Free Pen	2
Web Upload	2
Play Sound	2
Batch Mode	2
Drag and Drop	2	Completed in 0.9
Printing Preferences	2
Copy external image to add to existing image	2
Undo	Current
Migrate to GitHub
Check for Update on Start